AT2 TEAM PLAN: AI EARLY WARNING FOR RAINFALL-TRIGGERED LANDSLIDES IN NEPAL

Team number: #

Due: Friday 23 October, 11:59pm (report, video and reflections)

1. THE PROBLEM

Climate change is making monsoon rainfall more extreme, and extreme rain triggers landslides. Nepal suffers deadly landslides almost every monsoon. Current early warning relies largely on fixed rainfall thresholds (to verify with a source), which ignore how saturated the soil already is and how steep and unstable each slope is.

Anchor event for the report and video: [pick one specific Nepal landslide and confirm its facts from a credible source].

2. OUR SOLUTION IN ONE SENTENCE

An early-warning system that predicts where slopes are at risk and when they are likely to fail, then turns that risk into clear alerts and safe actions for local officials and residents.

Flash floods 

Alternatives: Forest fires, Hurricanes, Flash floods, Drought

3. THREE TECHNIQUES, ONE PROBLEM

Computer Vision

Sequential Models

Next-Generation Foundation Models

4. RUBRIC POINTS WE MUST HIT (marks are graded strictly to these)

Report (12 marks)

- Stakeholders and requirements: list end-users (district disaster officers, residents, government agencies) and derive functional, non-functional and societal requirements from their needs.

- Why AI is necessary: compare against fixed rainfall thresholds and manual monitoring, with evidence.

- Technique comparison (2.4 marks): one comparison across all three techniques on problem-relevant criteria.

- Data, architecture and workflow (2.4 marks): an architecture diagram and a workflow diagram showing where humans approve alerts and feed back.

- Evaluation and risks: measurable targets (e.g. recall on past events, false-alarm rate, warning lead time) and all six risk types: technical, social, ethical, legal, safety, misuse.

- Literature cited throughout, UTS APA.

Video (15 marks, worth more than the report)

- Aimed at end-users, not markers. Open with a family's evening before a landslide.

- Explain the user journey and each technique in plain language.

- Show honest limits and safeguards (false alarms, missed events, human sign-off on alerts).

- Good audio, purposeful visuals, every member on camera with balanced time.

Reflection (8 marks, individual)

- Specific, checkable evidence of what you did (sections, diagrams, video parts, dates).

- A peer review of each other member: specific and evidence-based.

- A realistic future role if the system were built.

5. REPORT STRUCTURE AND OWNERS

Template headings plus the sections the rubric needs. Put your name next to what you own.

- Executive summary (1 page, written last). Owner:

- Introduction: business context, problem statement, stakeholders, requirements. Owner:

- Proposal: aims and objectives, methodology, expected outcomes, benefits and why AI. Owner:

- Proposal: resources, risks, timeline, communication of outcomes. Owner:

- Solution design: one technique section each, plus the comparison and integration. Owners: A, B, C

- Implementation design: data strategy, architecture and workflow diagrams, tools. Owner:

- Evaluation design, plus ethics, legal, safety and misuse. Owner:

- Risk management (one mitigation per risk). Owner:

- References (UTS APA) and appendices. Owners: all

Length: 15-20 pages, Times New Roman 12, single spacing, standard margins.

6. TIMELINE

- Thu 15 - Fri 16 Oct: agree problem, anchor event and technique owners. Agree contribution split. Start progress log.

- Sat 17 - Sun 18 Oct: draft own sections. Shared technique comparison. Architecture and workflow diagrams.

- Mon 19 Oct: video script from the user scenario. Merge report draft.

- Tue 20 Oct: record video segments (each member separately, good mic). Edit.

- Wed 21 Oct: full report read-through for consistency and page count. Final video cut. Reflections drafted.

- Thu 22 Oct: buffer. Fixes, export PDF, upload video and test the link.

- Fri 23 Oct: submit everything well before 11:59pm.

7. SUBMISSION CHECKLIST

- Report: TeamNumber_AT2_report.pdf (one member uploads).

- Video: TeamNumber_AT2_video.mp4, hosted (unlisted YouTube or OneDrive) and the LINK pasted into Canvas. The folder takes a text entry, not a file. Test the link while logged out.

- Reflection, each of us: Surname_Firstname_TeamNumber_AT2_reflection.docx (the team number is required on Canvas).

- Peer review / contribution form emailed to the coordinator (confirm if required this year).

8. WORKING RULES

- Keep a dated progress log at the bottom of this doc: who did what, when. It is our evidence for the reflections.

- Use the same terms, numbers and diagrams in the report and the video.

- Turnitin similarity limit is 10%. Write in our own words and cite everything.

9. OPEN DECISIONS

[ ] Anchor landslide event

[ ] Member C's technique: language-model alerts or evacuation routing

[ ] Who owns each report section

[ ] Who edits the video and who submits

[ ] Contribution split, agreed in writing

PROGRESS LOG

Date / Member / Work done

-